## Sheet1
ID# | Training Item | Description | Reference # | Required Delivery Date | Responsible Authority | Status (R / Y / G)
1 | Training Requirements Planning Process Methodology (TRPPMM) / Front End Analysis (FEA) | TRPPM is a collection of discreet training requirement determination tasks resulting in the development of the technical program data,part I of the NTSP. Part I states that the underlying concepts that will govern operation, maintenacne, training, the quantity and quality ofpersonnel required, and the necessary training hardware. TRPPM is designed to provide manpower, personnel, & training (MPT) analysis with a set of tasks which will determine the best MPT acquisition profile or an alternative system concept early in the acquisition process. The task based approach to training requirements determination also provides PMs with the flexibility to tailor the level of training analysis that will be applied to their program. FEA is a structured process used to examine MPT requirements and identify alternative approaches to training job tasks. The process identifies job tasks to be performed, analyzes the skills and knowledge needed to perform them, assesses the technologies available for training the skills and knowedge, performs a media analysis to recommend the best mix of delivery media, and provides cost and lead-time comparisons fo the feasable alternatives. Requirement includes loading data into an applicable NTSP web site (e.g.; Aviation Technical Training (AVTECHTRA), Naval Sea System Training Acquisition (SEATRAQ), Navy Knowledge Online (NKO), Human Analysis Requirements Planning System (HARPS)). | OPNAV P-751-2-9-97, OPNAV P-751-3-9-97, OPNAVINST 1500.76B | Preliminary NTSP (Parts 1, 5, 7); FEA; Training Systems Requirement and Analysis (TSRA); Trainng Device Decision Coordinating Paper (TDDCP); Military Characteristics (MC) | Warfare Resource Sponsor
2a | Job Task Analysis (JTA) Validation | JTA is a product that provides a detailed listing of tasks necessary to perform a specific job or duty. Job related data should include its purpose, functional responsibility of personnel, required support equipment and materials, periodicity of tasks, and include system operations/maintenance and human systems integration factors. Requirements include validating the JTA and loading data into AVTECHTRA, SEATRAQ, NKO, or HARPS. | OPNAVINST 1500.76B | Prelim; Final; Update; | Warfare Resource Sponsor or TSA
2b | Job Duty Task Analysis (JDTA) validation | JDTA is the process that lists the job, duties, and tasks performed by individuals in operational fields. Job related data may include surveys and needs assesments, indicating a need to revise training. Requirements include validating the JDTA and loading data in (e.g.; AVTECHTRA, SEATRAQ, NKO, HARPS) | NETCINST 1510.4 | Prelim; Final; Update; | Warfare Resource Sponsor or TSA
3 | NTSP Approval | NTSPs are navy and integrated Navy/Marine Coprs documents which communicate MPT gaps and needs in support of new and/or modernization programs. Once a final or updated NTSP is approved by the resource advocate/sponsor, the NTSP shall be used as the offical record of the training planning process that facilitated enterprise(s) definition of the system's MPT requirements. Resource advocates/sponsors are required to obtain concurrance from Director, Education and Training (N15) for ACAT I programs, and Branch Chief Acquisition & Human Systems Integration (OPNAV N151) for ACAT II-V programs prior to approving a final or updated NTSP. | OPNAVINST 1500.76B, Approved NTSP | Prelim; MS B; (Final) Update; | Warfare Resource Sponsor
4 | Manpower Estimate (ME) Validation and Approval | ME is the primary document addressing manpower affordibility in terms of military end strength (including force structure, student end strength) and civilian work years. Include Human Systems Integration (HIS) requirements where an HIS plan exists, and ensure systems command has certified through technical authority. Requirement includes loading data into an applicable NTSP web site (e.g.; AVTECHTRA, SEATRAQ, NKO, HARPS). | DoDI 5000.02 of 2 Dec 2008, SECNAVINST 5000.2D, OPNAVINST 1000.16K | MS B; (Initial) MS C; (Update) Full Rate Production (FRP); (Update) | N1
5 | TSIP | (formerly Training Equipment Facility Requirement) is a plan prepared to: define facility requirements, including military construction (MILCON) and special projects, for installation of the training system; identify all associated logistic support elements; and transfer training ownership responsibility from the TSA to the TA. The TSIP is an integral part of the system acquisition process and supports introduction of new trainng systems and equipment, training system changes, and sustaining requirements. Close liaison between the TSA and TA is key in developing TSIPs to meet the established RFT date. | OPNAVINST 11102.2, OPNAVINST 1500.2B | Phase I: Phase II: Beneficial Occupancy Date (BOD) (If MILCON Required): RFT: | Warfare Resource Sponsor / TSA / TA
6a | Facilities Training Space MILCON | Identification of facilities (buildings, spaces, utilities, etc.) required and or available. Coordination of facility impacts with the host command and requesting MILCON, if required. Learning resource center funding and installation. | OPNAVINST 11102.2, NAVSO P-1000, OPNAVINST 11010.2)g | MILCON: Start Finsih Classroom | TA
6b | Facilities Training Space (Requirements and Funding) | TSA will provide facility data relative to trainer installation to the TA for the MILCON request and TSIP coordinaiton | NAVSO P-1000, OPNAVINST 1500.76B, Approved NTSP | Technical Training Equipment (TTE) (Install): RFT: | TSA
7 | Learning Objectives (for Non-Distributed Learning) | Learning objectives describe the full range of task proficiencies, skills and knowledge to be mastered by the trainee to achieve specified qualification level. Enabling, terminal, and supporting objectives describe the job behavior, conditions of performance, standards of performance, and test criterion. Requirement is TA concurrance and coordination with the program office and TSA that learning objectives are defined with the appropriate standards, and the knowledge, skills abilities, and media required to develop a learning program. | MIL-HDBK-29612-2A NAVEDTRA 130-134 | Training Project Plan: | TSA / TA
8 | Training Materials - Visual Information (TMVI) | TMVI products (includes still and motion picture photography, video recording with or without sound, graphic arts, visual aids, models, displays, visual presentation services, and the support processes) which the TSA deems necessary and that are called out in the deliverables shall be delivered through life cycle support. | NETCINST 1510.10B | RDD: | TSA
9 | Trainng Materials - Interactive Materials | Content delivered as part of interactive learning training (ILT), Computer Based Training (CBT) / Web-Based Training (WBT) / Interactive Learning Environment (ILE) that allows students to interact and receive feedback. Interactive multi-media instruction should be appropriate and cost effective to instruct, demonstrate, and practice the learning and performance required to achieve the learning outcome. All applicable interactive products are delivered by the TSA. | DoDI 1322.26 of 16 June 2006, OPNAVINST 1500.76B NETCINST 1510.10B | RDD: | Warfare Resource Sponsor / TSA
10 | TTE / TD Funding | Validate all development, procurement, operation, and support costs are prorammed and funded. Funding in place and contractor operated maintenance support. | NAVSO P-1000, NETCINST 4700.1 | RDD: | Warfare Resource Sponsor / TSA / TA
11 | TTE / TD | Investment cost end items of operational equipment, devoted to the training and instruction of Naval personnel, for which PMs have the responsibility for the design, development, modernization, configuration management, or selection for service or special use. Training devices are hardware and software which have been designed or modified exclusively for training purposes involving, to some degree, simulation or stimulation in its construction or operation, so as to demonstrate or illustrate a concept or simulate an operational circumstance or environment. Coordination of concurrency between the JTA and TTE must be approved before design and development. Scheduling of delivery, installation, and instructortraining is required. Training device software updates, configuration management, enginnering changes, and modernization are programmed by the acquisition warfare resource sponsor and executed by the TSA. Gaps in training devices must be addressed by TSA/TA | OPNAVINST 11102.2 OPNAVINST 1500.76B NAVSO P-1000 | RDD: | Warfare Resource Sponsor / TSA / TA
12a | TTE / TD Maintenance / Support | Government / contractor operation and maintenance support is to be provided for all training equipment in support of initial training. Initial training equipment and support items must take place prior to the program's initial operating capability (IOC) date or FRP decision. The training system has contractor operator maintenance support and/or integrated logistics suport plan in place. Support is to be provided for all training equipment whether in support of initial or follow-on training | NAVSO P-1000 OPNAVINST 1500.76B OPNAVINST 11102.2 | First convening of initial training | Warfare Resource Sponsor / TSA
12b | TTE / TD / Maintenance Tech Support | Government or contractor maintenance and technical support are to be provided for all training equipment in support of follow-on training. | NAVSO P-1000 OPNAVINST 1500.76B OPNAVINST 11102.2 | RFT | N1 / TA
13 | Training Effectiveness | Training Effectiveness Evaluation Plan (TEEP) is developed and in place, along with an analysis of trainng capability and potential value of the training system in enabling students to achieve program learning objectives. The TEEP is developed as applicable; to ensure that acquired training devices(s) meet the Military Service's trainng requirements and effectiveness levels. | OPNAVINST 1500.76B NAVSO P-1000, OPNAV P-751-1-9-97 | RDD; | Warfare Resource Sponsor / TSA / TA
14 | Curiculum Development | Guidance for curriculum development. JDTA guides Navy curriculum developers' guidance in developing accurate and effective training materials. These materials shall be approved by the TA and delivered by the TSA: (1) tasks to develop training materials (2) sequence of task performance, and (3) task performance responsibilities | NAVEDTRA 130-134 | RDD: | TSA / TA
15 | Instructor Materials | Instructor training, instructor services for initial class convening, guidance to instructors to conduct the courses and provide feedback to students. TSA is responsible for development of an instructor guide and the TA is responsible to develop wqays to encourage and motivate students, track and manage progress, and point out typical points of failure for remediation. Instructor material must be approved by TA, loaded into authoring instrucotor material database by the TSA/TA. | NAVEDTRA 130-134 OPNAVINST 1500.76B | RDD: | TSA / TA
16 | Training Guides / Materials | The trainee guide is the primary trainee material, contains knowledge and skill objectives | NAVEDTRA 130-134 | RDD: | TSA / TA
17 | Course Responsibility | Training Courseware / Curricula / Manuals transferred by Acquistion Program Management Office to the designated learning center or TA. | NETCINST 1510.1A | RDD: | TSA
18 | Course Management | Once the curriculum development process is completed or the program office transfers curriculum development efforts to the TA, the course management process begins. The course management process includes revisions to existing courses, course master schedule, Navy training quota management, etc. | NETCINST 1510.1A NAVEDTRA 135 | RDD: | N1/TA
19 | Distance Support | Distance support data will be delivered via secure intranet or other appropriate means. | OPNAVINST 5310.23 | RDD: | Warfare Resurce Sponsor / TSA / TA
20 | CBT / Embedded Ashore & Afloat Infrastructure | Capabilities built into, strapped onto, or plugged into operational material systems to train, sustain, and enhance individual and crew skill proficiencies necessary to operate and maintain the equipment. CBT and embedded training will be delivered by the TSA to support TA ashore and afloat infrastructure. | Defense Acquisition Guidebook, OPNAVINST 1540.51D, NAVEDTRA 136, DoDD 1322.18 of 13 Jan 2009 | RDD: | TSA
21 | Naval Education and Training Command (NETC) Business Plan | NETC ssignment of learning center or TA responsibilities to include Corporate Enterprise Training Activity Resource System (CeTARS) course identification number and course data processing establishment for tracking course management. | NETCINST 1510.10B | Training Project Plan (TPP): CETARS LOAD Date | TA
22 | Student Activities | NETC assignment of learning center or training authority responsibilites to documentin student activities through the training production pipeline. Items transioned in CeTARS and Training Requirements Management System (TRMS) | NETCINST 1510.1A | TPP: CETARS Date: TRMS Date: | TA
23 | Publications and Interactive Electronic Technical Manual (IETM) | Technical documentation for the system(s) that supplement and support training for procedures, installation, troubleshooting, and settings shall be delivered by the TSA. These include the IETM, software and diagnostic manuals. Operations manuals describe the systems on every ship; they are created and updated by a wide range of authoring, engineering personnel including manufacturers. Maintenance manuals describe the fault diagnosis and repair of systems; they are created and updated by a wide range of authoring, engineering and logistics personnel including manufacturers. If the TSA or PM is going to deliver IETMs, they must first ensure that the training facilities have adequate spare resources to use the IETMs (i.e.: electronic classrooms). If adequate spare resources do not exist at the training facility then the PM/TSA wil be responsible for providing an electronic classroom. | OPNAVINST 1500.76B, NAVSO P-1000 | RDD: | Warfare Resource Sponsor
24a | Accreditaion (Electronic Material Security Tempest Surveys | Facility certified for delivery of classified information and material. | OPNAVINST C5510.93F | Date Certified If Applicable: | TA
24b | Certification (Automated Data Processing (ADP) Security) | Facility certified for delivery of classified information and materuial. | OPNAVINST 5239.1C, NETCINST 5510.1 | Date Certified If Applicable: | TSA/TA
25 | On The Job Training (OJT) Handbook | The OJT Handbook consists of a single lesson or a series of lessons designed to support selected learning objectives transitioned provided by the TSA | NAVEDTRA 130-131 | RDD: | Warfare Resource Sponsor / TSA
26 | Individual Training Sustainment Funding | Military or civilain (including contractor) instructor requirements(manpower personnel navy (MPN) Operations & Maintenance Navy (OM&N) are programmed prior to concurrance on a final or updated NTSP where increases or new Navy Enslited Classification (NEC) producing courses are required for operators and maintainers of new or modernized systems. Funds to support and sustain the conduct of training delivered by the TSA have been programmed and budgeted. | SECNAVINST 5000.2D, OPNAVINST 1500.76B, NAVSO-P-1000 | RFT Date | N1/N4 as applicable / TA
27 | OM&N Temporary Additional Duty Travel Target (TADTAR) funding for units to attend installation related initial training by TSA and follow-on training "F" schools by TA | OM&N funds for training are provided to units by Director, Fleet Readiness Division (OPNAV N43) via United States Fleet Forces Command (USFLTFORCOM) and type commanders (TYCOMs). OPNAV N43 or designated agent USFLTFORCOM. TYCOMs shall endorse NTSPs where new, sustained OM&N increases is planned for training. (Note: Must consider impact on OPNAV N43 training OM&N TADTAR budget when choosing a training solution. Notify OPNAV N43 via TYCOMs and USFLTFORCOM if a new training system will obligate increases in OM&N TADTAR requirements for units to attend initial and follow-on training such as "F" schools.) | NAVSO P-1000 Section 074201, OPNAVINST 1500.76B |  | N4
28 | Individual account (IA) funding for personnel to attend follow-on training "C" schools and changes to "A" schools. | Temporary duty instruction and IA funds for en route training are programmed for new IA account increases by N1. N1 or designated agent nsures funding is programmed prior to concurrance on a final or updated NTSP. | NAVSO P-1000 Section 074201 |  | N1/N4 as applicable
20 | RFT | The date a training syste and its associated logistics, maintenance, syllabus, and instructors are certified to be available for training at the learning facility. This date is predicated on the availability of a new, modified, or rehabilitated learning facility for training purposes. All aspects of the facility must be ready including building completion, completed site preparation, training system installation and testing, trained instructors, furnishings, e.g.; non-technical collateral equipment. This is the ultimate planning date for the new, modified, and changed training system and its readiness for use. | OPNAVINST 1500.76B | Primary: Secondary: Iterative: | TSA/TA Warfare Resource Sponsor

## Sheet2
Color Code
Red | Training System Is Not programmed in POM or is unfunded to meet RDD or the deadline established by governing issuance. Mitigation response and corrective action required
Yellow | Trainng system requirement is programmed in POMN, funded, but behind schedule to meet RDD. Mitigation response and corrective action required.
Green | Training system requirement is funded and on schedule to meet RDD